## Sheet1
Sr. No. | Week | Start Date | End Date | Planned Activity | Status | Comments | Suggestions (Avinash Sir / Shahin Mam)
1 | Week 1 (9 July to 17 July) | 2025-09-07 | 2025-09-07 | Research Web Speech API for STT | Completed
2 |  | 2025-10-07 | 2025-10-07 | Research SpeechSynthesis for TTS | Completed | Use natural voice tones | As per Ma'am's suggestion, exploring AI tools and libraries
3 |  | 2025-11-07 | 2025-11-07 | Evaluate NLP Tools (OpenAI, Dialogflow, Wit.ai) | Completed |  | for implementing speech recognition (e.g., Web Speech API
4 |  | 14/07/2025 | 14/07/2025 | Design user flow (voice → NLP → confirm → action) | Completed |  | , OpenAI Whisper, etc.).
5 |  | 15/07/2025 | 15/07/2025 | Design Home, Mic button, Confirmation & Error modals | Completed
6 |  | 16/07/2025 | 16/07/2025 | Layout for live transcript | Completed
7 |  | 17/07/2025 | 17/07/2025 | Review progress, document tech stack & flows | Completed
8
9
10 | Week 2 (18 July to 25 July) | 18/07/2025 | 18/07/2025 | Create frontend skeleton and folder structure | Completed
11 |  | 21/07/2025 | 21/07/2025 | Setup styling framework and test responsiveness | Completed
12 |  | 22/07/2025 | 22/07/2025 | Setup navigation and placeholder components (Home, etc.) | Completed |  | This is a static demo; Sir suggested making it dynamic
13 |  | 23/07/2025 | 23/07/2025 | Create mic input component + icon toggle | Completed | Voice + Text dual flow | so it can be reused anywhere on the website as needed
14 |  | 24/07/2025 | 24/07/2025 | Integrate Web Speech API and show live transcription | Completed
15 |  | 25/07/2025 | 25/07/2025 | Textarea | Completed
16
17
18 | Week 3 (28 July to 4 August) | 28/07/2025 | 28/07/2025 | Integrate NLP engine | Planned
19 |  | 29/07/2025 | 29/07/2025 | Detect and fill any textarea/form | Planned | Test with real examples
20 |  | 30/07/2025 | 30/07/2025 | Implement dynamic voice control | Planned
21 |  | 31/07/2025 | 31/07/2025 | Use SpeechSynthesis API to read booking confirmation | Planned | Include fallback messages
22 |  | 2025-01-08 | 2025-01-08 | Build UI to view/edit/cancel appointments | Planned | Card view or table layout
23 |  | 2025-04-08 | 2025-04-08 | Recognize cancel/reschedule commands via voice | Planned
24
25
26 | Week 4 (5 Aug to 9 Aug) | 2025-05-08 | 2025-05-08 | Add logic for "no input", "not understood", or ambiguous time like "next Monday" | Planned | Use fallback prompts
27 |  | 2025-06-08 | 2025-06-08 | Test intent matching + accuracy of doctor/date/time extraction | Planned | Test multiple accents
28 |  | 2025-07-08 | 2025-07-08 | Add mic glow animation, visual feedback, error badges | Planned | Add keyboard accessibility
29 |  | 2025-08-08 | 2025-08-08 | Connect to backend if any, finalize all modules | Planned | Make code production-ready
30 |  | 2025-09-08 | 2025-09-08 | Prepare for deployment | Planned | Include usage screenshots